## Cover
LEAR PROPRIETARY AND CONFIDENTIAL - The information contained herein is the exclusive property of Lear Corporation. This data shall not be disseminated or republished without prior written consent of Lear Corporation
REFERENCE:
SDP_CL-SW-362.xls
| APPROVED BY: | PROJECT:
| Process CCB | SSE Process
AUTHORIZED AUDIENCE: INTERNAL | Software Delivery Procedure Checklist
Document History
Version | Comments | Date (dd/mm/yy) | Author
0.1 | Frist draft of Checklist template | 2008-08-20 | J. Gubianes
1.5 | Migrated from SW984-362-14.doc document and included Synergy Delivery process | 2009-01-13 | J. Gubianes
1.6 | Note on the applicability of section 2 added | 2009-01-13 | J. Gubianes
1.7 | Updated of the references to standard documentation according with new naming conventions. | 2010-08-20 | F.Graffigna
1.8 | Updated 362 Delivery checklist process template for JIRA | 2010-08-30 | F.Graffigna
1.9 | Template fully adapted to JIRA / SVN | 2010-09-13 | F.Graffigna
1.10 | Variable creation. 303 check for JIRA/ SVN moved to "Load code" sheet Step 2 Renamed as Start of the Delivery Process | 2010-10-28 | F.Graffigna
1.11 | Included Customer Responsible information | 2010-11-08 | J. Gubianes
1.12 | Reference to fill in the "Board Approval Process Check List" when delivery enters NM process added | 2011-04-28 | M. Biarge J. Orts
1.13 | Included check in sheet 3 to verify PNs once generated the vbfs files | 2014-10-02 | M.Borao
1.14 | Modified point 103 in order to take into account the issues accepted as it is to be reported in SDD-360 in case of confirmation from SWTL side | 2014-10-02 | M.Borao
0.12 | [PROCESS-10836] Updated header fields according to the new LEAR organization. Change log numbering corrected. Typos correction | 2017-07-14 | G.Figuerola
0.13 | [PROCESS-10939] Changed 5 references of standard file names. | 2017-08-21 | G.Figuerola
0.14 | [PROCESS-11003] Replace "Validation" by "System Test" in all process documentation | 2017-10-24 | G.Figuerola
0.15 | [PROCESS-10037] Removal of the obsolete SMKT-SW-366.xls referece, | 2018-06-01 | G.Figuerola
0.16 | [PROCESS-11835] Added check 108 | 2019-06-07 | G.Figuerola
0.17 | [PROCESS-11835] Added in the check 108 that this has to be done once per phase, not at every release | 2019-10-14 | C. Tapias
0.18 | [PROCESS-11582] "Implemented SW Issues" and "SW changes review" tabs joined in new one called "Implemented SW Changes" | 2020-04-30 | C. Tapias
0.19 | [PROCESS-10050] Added Approve SW Releaes tab and work flow in the cover updated. | 2020-04-30 | C. Tapias
0.2 | [PROCESS-10050] Added SEM steps for SW2,3,4. removed reference to CBAP (step 802), removed references to synergy/sourcesafe in the comments, moved the 700 to the end of step 6th, as it is needed to approve the release. Added tab 9 for sem release approval | 2020-04-30 | C. Tapias
0.21 | [PROCESS-10050] renamed tab 5 to SW Release Acceptance Test | 2020-05-22 | C. Tapias
0.22 | [PROCESS-11906] added note about the confirmation of receipt (steps 1004, 1005, 708) [PROCESS-10726] add Doors check in step 213 | 2020-05-22 | C. Tapias
Work Flow Build Delivery Strategy
Table of Contents:
0.- Delivery Information
1.- Preparation
2.- Start Of Delivery Process
3. - RC (Release Candidate)
4.- Load Code
5.- SW Release Acceptance Test
6. - SW Team Leader approval
7.- RC acceptance
8.- Testing
9.- Approve SW Release
10.- Release
Rules of Template use:
- When taking to use it in a specific PROJECT:
+ Change the title (Delete "Template")
+ Change the project name
+ Change the reference as the file name has to change to
a project specific.
+ Change the Authorized Audience if necessary (if document
is for customer, subcontractor, etc...)
+ If the History Log is not necessary for the project document, delete it.
+ Include any other neccesary information specific of the project, like
Software Version, etc…
+ The sheet "Table of contents" gives a brief description of the different
sheets that are included in the book. This sheet is optional, depending
on the specific document. If there is place for the Table of
contents in this cover sheet, place it here, to save one sheet.
- When modifying the TEMPLATE:
+ The History Log is necessary to keep trak of changes in the
TEMPLATE, so use it as indicated in the Software
Documentation Guidelines
+ Keep the version updated as indicated in in the Software
Documentation Guidelines
2.- Start of Delivery Process
Resp: Build Manager
3.-Release Candidate
Resp: Build Manager
4.- Load code to the target
Resp: Build Manager
1.-Preparation
Resp: Build Manager
Is it OK?
NO
Yes
6.- Approve SW Release
Resp: SW Team Leader
Yes
NO
7.-Release Candidate acceptance
Resp: Build Manager
5.- SW Release Acceptance Test
Resp: Build Manager
Release Approved?
8.-System Testing.
Resp: System Test Team
Is it OK?
9.-Approve SW Release.
Resp: SWTL
Yes
NO
10.-Release.
Resp: Build Manager

## 0.- Delivery Information
0.- Delivery Information
Version X | <Version X>
Version Y | <Version Y>
Version Z | <Version Z>
CV | <CV>
Delivery Author: | Charles Peacock
Delivery Date: | 2020-08-10
Delivery to System Test Date: | 2021-07-20
Project: | Ford SDLC
Baseline: | LJ6T-14F530-BJ (R19V11)
Delivery Folder: | http://esvls-svn01.corp.lear.com/svn/SW_FORD_CX482_3_SDLC/trunk/07_RELEASE/CX482-3/17-BJ/05-Production_6719-Jul-2021
Temporal NM Folder: | <Delivery_Folder>
Software Team Leader: | Charles Peacock
Software Team Leader E-mail: | cpeacock@lear.com
Build Manager: | Charles Peacock
Build Manager E-mail: | cpeacock@lear.com
System Test Responsible | Kamini Patil
System Test Responsible E-mail: | KPatil02@lear.com
Customer Responsible | Rachana Dasari
Customer Responsible E-mail: | rdasari5@ford.com
P/N's for this Release |  | File
SIGNAL CONFIG FILE P/N |  | LJ6T-14F535-BK
APP P/N |  | LJ6T-14F530-BK
DGN SPECS VER |  | DSLU5T-14F642-BAD
Lear version |  | 6919-Jul-2021
Secondary Bootloader |  | LU5T-14F532-BAA
Deliverables
SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx | SW Version History
SCMP-SW-160.doc | SW Configuration Management Plan
SVTR-SW-310.xls | System Test Report
SDD-SW-360_Ford_SDLC_LJ6T-14F530-BK.xlsx | Software Delivery Document
SDP_CL-SW-362_Ford_SDLC_LJ6T-14F530-BK.xlsx | SW Delivery Checklist
SDMR-SW-363_Ford_SDLC_LJ6T-14F530-BK.xlsm | Software Delivery Memory Report
SPP-SW-120.doc | Software Project Plan

## 1.-Preparation
1.- Start of Delivery Process
Task Responsible : Charles Peacock |  |  | Support Column
Task Timing Info : One day before delivery date (44053) process is planned. |  |  | (Use it for copy, send e-mail, etc)
Item | Task | DONE Y/N
100 | Check the P/N (Part Number) applicable for the release. If some doubt raises, send an e-mail to <Responsible> [Responsible@email.com] to request eventual clarification about the release P/N. |  | <Responsible> [Responsible@email.com]
101 | Ensure cover sheet of this doc contains all information required for this release.
102 | Send a Communication to Software Development Team members. Subject: [<Project Name>] Please, be sure to complete your tasks and resolve your CR's for release v<Version X>.<Version Y>.<Version Z>(<CV>).Due date [Two days before delivery process is planned]
103 | Ask if all SW Engineers have committed all needed files for current version and if they have closed all JIRA tickets. Any current deviation to specs or outstanding defect must be introduced in JIRA/181 to reflect current release status. Send a Communication to the Team people (e-mail, phone, etc…): <TEAM MAIL LIST> Subject: Please check in everything needed for the today's vX.Y.Z(CV) delivery and update all related docs. I expect your early reply. X.Y.Z: Lear version CV: Customer version Example: v1.4.0(B2.0) Ask SWTL if in all related docs we should include the also the issues in: I. Resolution = accepted as it is & Approved by: Customer II. Approval = YES & Approved by= Customer & Status Root Cause Found or Accepted. X.Y.Z: Lear version CV: Customer version Example: v1.4.0(B2.0)
100 | "Review if all SW Engineers have checked in all needed files for this version and if they have updated all relative documentation: - "&Software_Delivery_Document&" - "&Software_Changes_Status_Summary
103 | Create a CR's assigned to the Build Manager for Integration Activities
104 | When ALL TEAM members has included all the release tasks in JIRA, perform the following actions: Review all release related tasks
105 | Review and conclude the release associated CR's
106 | Send a mail to the release Build Manager including the P/N Subject : [Ford SDLC] Tasks and CR's reviewed and ready to be integrated for version FEM_v<Version X>.<Version Y>.<Version Z>(<CV>) P/N info below.
107 | - Scan the software using Lear standard scanning tool (FNCI) - Compare the results with the currently approved Open Source Software - inform SW Team Leader and Open Source Coordinator about any new/changed Open Source Software vulnerabilities. - inform SW Team Leader and Open Source Coordinator about any new/changed third-party software, in order to ensure that it is appropriately licensed. Note: In step 306 of this document, the scanning results will be recorded in the Delivery Document (SDD-SW-360.xlsx), "Open Source Software disclosure" tab |  | only in case release to customer (E3, P1, P2, P3),
108 | The build manager has to fill, at least once per phase, column Z "work product status" in WP 600 using following criteria: - if document has to be approved (column R "Needs Agreement / Approval?"=YES from WP 600), open the corresponding WP and see in cover history log whether the first digit has changed=> in this case the status is "reviewed". - if document does not need approval, then set status as following: "draft" if first digit is 0.x "updated" if first digit is >=1.x - if document does not exist, then leave status empty. | N/A | SW deleloped under previous process - no WP 600 exists
N/A
Y
N

## 2.- Start of Delivery Process
3.- SW Changes Review
Task Responsible : Charles Peacock |  |  | Support Column
Task Timing Info : Date of release (44053). |  |  | (Use it for copy, send e-mail, etc)
Item |  | DONE Y/N
200 | List all files that have changed since las delivery to customer | y | This section is mandatory for production releases (SW3, SW4). Nevertheless any indication respect to this section shall be documented in the "SW & System Project Plan" (SPP-SW-120) To list all changes, you can use the SW Change History & Stability Index Report (SCHSIR-SW-162)
202 | Organize a review meeting to review all changes made to the source code from previous customer delivered SW version At least the attendance shall be: - SW Team Leader (to Lead the meeting) - SW Engineer responsible for the file(s) changed (can attend one by one) - Senior SW Engineer (not necessarily from the project) Agenda: - Review all REAL changes made to the code against customer Specification and Product Change Requests (PCRs). Note: ONLY changes agreed with the customer will be approved. | y
205 | Include a list with approved changes into the SW delivery document (SDD-SW-360_Ford_SDLC_LJ6T-14F530-BK.xlsx) in sheet "Implemented SW Changes" | y
206 | Check if SW changes have an impact on the End Of Line (EOL) Test Specification and update that End Of Line (EOL) Test Specification accordingly (SW Team Leader to support build manager for this task). | y
207 | Create the release folder in Delivery_Folder |  | Yes - pulldown not working
209 | Add SDP_CL-SW-362_Ford_SDLC_LJ6T-14F530-BK.xlsx and SDD-SW-360_Ford_SDLC_LJ6T-14F530-BK.xlsx under Delivery_Folder |  | Yes - pulldown not working
210 | Include on <Delivery_Folder> folder structure according with SCMP-SW-160.doc |  | Yes - pulldown not working
211 | Check that <TEAM MEMBER1>has committed all theirs files in the SVN and won't modify the files during the delivery process. The confirmation must be by either email or phone. |  | Yes - pulldown not working
| Check that <TEAM MEMBER2>has committed all theirs files in the SVN and won't modify the files during the delivery process. The confirmation must be by either email or phone. |  | N/A
| … |  | N/A
| Check that <TEAM MEMBERN>has committed all theirs files in the SVN and won't modify the files during the delivery process. The confirmation must be by either email or phone. |  | N/A
212 | Check that all the JIRA tickets related to SW Change, SW Defects or SW Implementation SubTasks have been reached to states Resolved (Ready for Validating), Closed or Rejected. Note every single found ticket reference that is not closed: <Non-closed tickets> If there are rejected issues confirm their apporval with SW Team Leader or Coordinator. |  | Yes - pulldown not working
213 | Check in DOORS that all SW requirements assigned to the releaes have been implemented. |  | Yes - pulldown not working
214 | If not done until now according Timing, please ask SWTL to create JIRA ticket for the release with title: Release [Integration][Loop][X.Y.Z][code version] and assign to SW Build Manager |  | Yes - pulldown not working
215 | Ask SWTL to confirm that he agrees on proceeding with the release. Subject : ["&Project&"] Tasks and CR's reviewed and ready to be integrated for [Integration][Loop][X.Y.Z][code version]" |  | Yes - pulldown not working
216 | Confirm acceptance of JIRA ticket for the release (move the JIRA ticket to accepted) |  | Yes - pulldown not working
Y
N

## 3.-RC
3.- Generating Release documentation.
Task Responsible : Charles Peacock |  |  | Support Column
Task Timing Info : 44397 |  |  | (Use it for copy, send e-mail, etc)
Item |  | DONE Y/N
301 | Check out the SW Version History (SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx) document. Update SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx and commit changes in SVN with the JIRA ticket of the release | Y
| Make sure internal version number is increased from last labelled version, and that it has not been labelled in a different ranch, refer to the SW Version History (SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx) document. | Y
302 | Include the SW Version History Log (SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx) document in <Delivery_Folder> | Y
303 | Copy the SW Memory Report (SDMR-SW-363_Ford_SDLC_LJ6T-14F530-BK.xlsm) template located in docs\01_General into the <Delivery_Folder> folder and name it for this release. Place the result of the map conversion into this file. | Y | In case of SW2,3,4
304 | Update the information of the different sheets of the SW Memory Report (SDMR-SW-363_Ford_SDLC_LJ6T-14F530-BK.xlsm) document. | Y | In case of SW2,3,4
305 | Prepare Software Delivery Document (SDD-SW-360_Ford_SDLC_LJ6T-14F530-BK.xlsx): <Version X>.<Version Y>.<Version Z>(<CV>) | Y
306 | Fullfill Software Delivery Document ("&Software_Delivery_Document&") for the release. - Check the P/N (from SW Version History "&SW_Version_History&") - Review specification reference list - List deviations from the intended functionailities to be included. - In case release to customer, fill the tab "Open Source Software Disclosure" with the results from FNCI scanning (see item 107 in this document) and send it to the Open Source Coordinator for approval | Y
N/A
Y
N

## 4.-Load code
4.- Generating Release documentation.
Task Responsible : Charles Peacock |  |  | Support Column
Task Timing Info : Date of release (44053). |  |  | (Use it for copy, send e-mail, etc)
Item |  | DONE Y/N
303 | Make a branch, copy the \trunk to <BRANCH RELEASE PATH> space intended for the relase | Y
| Get the 01_Code files from Branch version created into a new local folder in your PC. i.e.:C:\DELIVERY\CodevXYZ | N/A | Built in Subversion folder - SDLC will not build in local folder
| Build the application from the new local folder created (follow the build procedure stated in SPP-SW-120.doc) | N/A | Built in Subversion folder - SDLC will not build in local folder
N/A
Y
N

## 5.- SW Release Acceptance Test
5.- Software Release Acceptance Test
Task Responsible : Charles Peacock |  |  | Support Column
Task Timing Info : Date of release to System Test team (44397) |  |  | (Use it for copy, send e-mail, etc)
Item |  | DONE Y/N
500 | Do the integration test in the target. |  | Yes (Column 3 only accepts blank data)
501 | Store Smoke Test script (SW Release acceptance test) inside under the delivery folder <Delivery_Folder> |  | Yes (Column 3 only accepts blank data)
502 | Check into <Delivery_Folder>, the the local delivery folder with all contents. |  | Yes (Column 3 only accepts blank data)
| Create inside the <TAG RELEASE PATH> folder the screenshot of the branch used for the release, and named it. |  | Yes (Column 3 only accepts blank data)
| Commit to SVN, into <Delivery_Folder> the local delivery folder with all contents. |  | Yes (Column 3 only accepts blank data)
N/A
Y
N

## 6.-SWTL Approval
6.- SWTL approval
Task Responsible : Charles Peacock |  |  | Support Column
Task Timing Info : Date of release to System Test team (44397) |  |  | (Use it for copy, send e-mail, etc)
Item |  | YES / NO
600 | The Software Delivery Document (SDD-SW-360-PPP) contains the list of changes implemented in this release, as well as all known defects. | Y
601 | All planned changes for this release are included in the software release. | Y
602 | All constraints/disclaimers are documented in the release notes. (Ex.: Not for saleable vehicles, Only valid with HW P/N xxx, etc.) | Y
603 | The Delivery Type information is documented in the Software Version History (SVH-SW-161-PPP). | Y
604 | The application and/or bootloader executables are included in this release. | Y | Application and bootloader delivered as a single S19 file
605 | Has SW Release acceptance test been successfully passed as part of release process? | Y
606 | RELEASE APPROVED? | Y | If not, explain the reasons.
Y
N

## 7.- RC acceptance
7.- Release Candidate Acceptance
Task Responsible : Charles Peacock |  |  | Support Column
Task Timing Info : Date of release to System Test team (44397) |  |  | (Use it for copy, send e-mail, etc)
Item |  | DONE Y/N
701 | Sent a mail to all the members of the team that the delivery has been done and congratulate them for their effort With Subject instead: [<Project Name>] Delivery process finished. Thanks everybody! Note: You can easily do this using the following hyperlink Project Sw Team | Y
703 | Save the local copy of this file with the name: SDP_CL-SW-362_Ford_SDLC_LJ6T-14F530-BK.xlsx and update this document to <CM TOOL NAME>, folder \<Delivery_Folder> | Y
704 | Update SW Version History document (SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx) in \01_General\ and match Delivery Information Sheet. NOTE: This file is intended to be updated for every release independently if the release is a RC or a customer Release. | Y | File is saved in …\trunk\03_GENERAL\SW161-SVH\CX482
706 | Take a copy of the SW files(SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx) from \01_General\ folder and update it into the SW Version history Document (SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx) document in the current <Delivery_Folder> | Y
707 | Sent a mail to the Team Leader, System Test Team Responsible, Project Leader and SQA that the delivery is finished and ready to start the System Test process. e.g. of subject: [<Ford SDLC>] Software vX.Y.Z(X.Y) ready to validate X.Y.Z: Lear version CV: Customer version | Y | In case release recipient is not System Test, do not include System Test Leader in the mail
708 | In case of SW1 to be sent to customer, ask the SWTL to send the Release to customer (Add in this step how the SW is sent to customer in case of SW1) | N/A | EPL to be informed Confirmation of receipt is needed. May be achieved electronically, by telephone, etc..
Y
N

## 8.-Testing
8.- Finishing System Test Process
Task Responsible : Kamini Patil & Charles Peacock |  |  | Support Column
Task Timing Info : At the end of System Test process |  |  | (Use it for copy, send e-mail, etc)
Item |  | DONE Y/N
803 | Upload Software Delivery Document SDD-SW-360_Ford_SDLC_LJ6T-14F530-BK.xlsx for the current delivery in <Delivery_Folder> | Y | Responsible: Build Manager
804 | Send an email to the whole team (Development and System Test): e.g. of subject: Subject: [Ford SDLC] Baseline v<Version X>.<Version Y>.<Version Z>(<CV>) System Test process finished. All related documentation in SVN. Thanks !! | Y | Responsible: Build Manager
805 | Send an email to SW Team Leader & Build Manager: e.g. of subject: Subject: [Ford SDLC] Baseline v<Version X>.<Version Y>.<Version Z>(<CV>) System Test process finished. Please baseline (whole project) System Test, Documents and Tools folders. Thanks !! | Y | Responsible: system test leader
806 | Build Manager: Baseline whole project done in <CM TOOL NAME> | Y | Responsible: Build Manager
N/A
Y
N

## 9.- Approve SW Release
9.-Approve SW Release
Task Responsible : Charles Peacock |  |  | Support Column
Task Timing Info : Date of release (<DELIVERY DATE>). |  |  | (Use it for copy, send e-mail, etc)
Item |  | DONE Y/N
900 | Create SEM Document, SEM SW Part Number and SEM SCN following guidelines | Y | This step is valid for SW2,3,4. See guidelines here
901 | Execute SWTL checklist and sign off the SCN | Y
902 | Wait until SW is approved by all stakeholders (wait until SCN is released) Note: you will receive a mail from SEM when the SCN is released | Y
N/A
Y
N

## 10.- Release
10.-Release (JIRA)
Task Responsible : Charles Peacock & Charles Peacock |  |  | Support Column
Task Timing Info : Date of release (<DELIVERY DATE>). |  |  | (Use it for copy, send e-mail, etc)
Item |  | DONE Y/N
1000 | Check that all the JIRA tickets related to SW Change, SW Defects or SW Implementation SubTasks for this release have been reached to states Open (Ready for Validating), Closed or Rejected. (Eg: Filter Project: Project X Issue Type: [LEAR] SW Defect, [LEAR] SW Change, [LEAR] PCR, [LEAR] Defect Root Cause Analysis Sub-Task, [LEAR] SW Implementation Sub-Task Fix For: [SW2] Loop 1 Resolutions: Unresolved returns = 0 tickets) | Y | Task Responsible : Charles Peacock
1001 | Move all remaining (unresolved) tasks to next release. | Y | Task Responsible : Charles Peacock
1002 | Perform release for current release: [Integration][Loop][X.Y.Z][code version] (In JIRA go to: project- version-manage versions. Choose our release and press release (operations) - Edit the Release name in, including the SW version identification in the name, for future reference. - Confirm the release data. |  | Task Responsible : Charles Peacock
1003 | Update the SW Version History document (SVH-SW-161_Ford_SDLC_LJ6T-14F530-BK.xlsx) with the current Release Name, and also the related TAG in SVN. | Y | Task Responsible : Charles Peacock
1004 | For SW2 to Customer, when SW Release is approved (SCN is released), SW can be sent to cusotmer (Add in this step how the SW is sent to customer in case of SW2). Confirmation of receipt is needed. May be achieved electronically, by telephone, etc.. When submitting the software package to the Customer, consider if needed to ask for customer approval for production. This is done for SW Releases type 2, that are candidate for being SW3/SW4 (production Release) Note: For SW2 to manufacturing plant, do nothing. The SW Release will be polled by manufacturing from SEM when SW Release is approved (SCN is released) Note: For SW3, do nothing. The SW Released will be polled by manufacturing from SEM when CBAP is approved | Y | Task Responsible : Charles Peacock
1005 | For SW4, wait until CBAP is approved, and then send SW to customer (Add in this step how the SW is sent to customer in case of SW4). Confirmation of receipt is needed. May be achieved electronically, by telephone, etc.. | Y | Task Responsible : Charles Peacock
1006
N/A
Y
N